## Sheet1
[17 empty] | Sourcing to drive | FTR tech to track
[11 empty] | 57 | 71 | 85 | 112 | 126 | 140 | 119 | 133 | 147 | 154 |  | 161 | 168 | 175 |  |  | 172
Drop | Month | Range | Opt Plan | Launch | Prod start | Prod end | Ex-fact 1 | Ex-fac end | Ship 1st | Ship last | PO Raise 45 | PO Raise 60 | PO Raise 75 | PO Raise 105 | PO Raise 105 | PO Raise 120 | Blue Seal 2 vendors submission | 1st Blue Seal Reviews | Trevor - SR | Internal SR | Techpak to Vendor | Tech pk handovr to Tech | Techpack by Design | VSR | VSR Working | Bottoms Workshop | Season Fabric Edit
D00 | Dec | Top-Up | - | 2026-12-31 | 2026-11-13 | 2026-12-11 | 2026-11-27 | 2026-12-02 | 2026-12-11 | 2026-12-16 | 2026-11-04 | 2026-10-21 | 2026-10-07 | 2026-09-10 | 2026-08-27 | 2026-08-13 | 2026-09-03 | 2026-08-27 | 2026-08-20 | 2026-08-13 | 2026-07-24 | 2026-07-17 | 2026-07-13 | 2026-07-12 | 2026-07-02 | 2026-06-17 | 2026-05-28
D01 | Jan | Essentials | 0 | 2027-01-07 | 2026-11-20 | 2026-12-18 | 2026-12-04 | 2026-12-09 | 2026-12-18 | 2026-12-23 | 2026-11-11 | 2026-10-28 | 2026-10-14 | 2026-09-17 | 2026-09-03 | 2026-08-20 | 2026-09-10 | 2026-09-03 | 2026-09-02 | 2026-09-01 | 2026-08-12 | 2026-08-05 | 2026-08-01 | 2026-07-31 | 2026-07-24 | 2026-07-12 | 2026-07-02
D02 | Jan | - | 124 | 2027-01-14 | 2026-11-27 | 2026-12-25 | 2026-12-11 | 2026-12-16 | 2026-12-25 | 2026-12-30 | 2026-11-18 | 2026-11-04 | 2026-10-21 | 2026-09-24 | 2026-09-10 | 2026-08-27 | 2026-09-17 | 2026-09-10 | 2026-09-02 | 2026-09-01 | 2026-08-12 | 2026-08-05 | 2026-08-01 | 2026-07-31 | 2026-07-24 | 2026-07-12 | 2026-07-02
D03 | Jan | Collection | 134 | 2027-01-21 | 2026-12-04 | 2027-01-01 | 2026-12-18 | 2026-12-23 | 2027-01-01 | 2027-01-06 | 2026-11-25 | 2026-11-11 | 2026-10-28 | 2026-10-01 | 2026-09-17 | 2026-09-03 | 2026-09-24 | 2026-09-17 | 2026-09-16 | 2026-09-15 | 2026-08-26 | 2026-08-19 | 2026-08-15 | 2026-07-31 | 2026-07-24 | 2026-07-12 | 2026-07-02
D04 | Jan | - | 28 | 2027-01-28 | 2026-12-11 | 2027-01-08 | 2026-12-25 | 2026-12-30 | 2027-01-08 | 2027-01-13 | 2026-12-02 | 2026-11-18 | 2026-11-04 | 2026-10-08 | 2026-09-24 | 2026-09-10 | 2026-10-01 | 2026-09-24 | 2026-09-16 | 2026-09-15 | 2026-08-26 | 2026-08-19 | 2026-08-15 | 2026-07-31 | 2026-07-24 | 2026-07-12 | 2026-07-02
D05 | Feb | Essentials | 0 | 2027-02-04 | 2026-12-18 | 2027-01-15 | 2027-01-01 | 2027-01-06 | 2027-01-15 | 2027-01-20 | 2026-12-09 | 2026-11-25 | 2026-11-11 | 2026-10-15 | 2026-10-01 | 2026-09-17 | 2026-10-08 | 2026-10-01 | 2026-09-30 | 2026-09-29 | 2026-09-09 | 2026-09-02 | 2026-08-29 | 2026-08-28 | 2026-08-21 | 2026-08-09 | 2026-07-30
D06 | Feb | - | 124 | 2027-02-11 | 2026-12-25 | 2027-01-22 | 2027-01-08 | 2027-01-13 | 2027-01-22 | 2027-01-27 | 2026-12-16 | 2026-12-02 | 2026-11-18 | 2026-10-22 | 2026-10-08 | 2026-09-24 | 2026-10-15 | 2026-10-08 | 2026-09-30 | 2026-09-29 | 2026-09-09 | 2026-09-02 | 2026-08-29 | 2026-08-28 | 2026-08-21 | 2026-08-09 | 2026-07-30
D07 | Feb | Collection | 134 | 2027-02-18 | 2027-01-01 | 2027-01-29 | 2027-01-15 | 2027-01-20 | 2027-01-29 | 2027-02-03 | 2026-12-23 | 2026-12-09 | 2026-11-25 | 2026-10-29 | 2026-10-15 | 2026-10-01 | 2026-10-22 | 2026-10-15 | 2026-10-14 | 2026-10-13 | 2026-09-23 | 2026-09-16 | 2026-09-12 | 2026-08-28 | 2026-08-21 | 2026-08-09 | 2026-07-30
D08 | Feb | - | 28 | 2027-02-25 | 2027-01-08 | 2027-02-05 | 2027-01-22 | 2027-01-27 | 2027-02-05 | 2027-02-10 | 2026-12-30 | 2026-12-16 | 2026-12-02 | 2026-11-05 | 2026-10-22 | 2026-10-08 | 2026-10-29 | 2026-10-22 | 2026-10-14 | 2026-10-13 | 2026-09-23 | 2026-09-16 | 2026-09-12 | 2026-08-28 | 2026-08-21 | 2026-08-09 | 2026-07-30
D09 | Mar | Essentials | 0 | 2027-03-04 | 2027-01-15 | 2027-02-12 | 2027-01-29 | 2027-02-03 | 2027-02-12 | 2027-02-17 | 2027-01-06 | 2026-12-23 | 2026-12-09 | 2026-11-12 | 2026-10-29 | 2026-10-15 | 2026-11-05 | 2026-10-29 | 2026-10-28 | 2026-10-27 | 2026-10-07 | 2026-09-30 | 2026-09-26 | 2026-09-25 | 2026-09-18 | 2026-09-06 | 2026-08-27
D10 | Mar | - | 124 | 2027-03-11 | 2027-01-22 | 2027-02-19 | 2027-02-05 | 2027-02-10 | 2027-02-19 | 2027-02-24 | 2027-01-13 | 2026-12-30 | 2026-12-16 | 2026-11-19 | 2026-11-05 | 2026-10-22 | 2026-11-12 | 2026-11-05 | 2026-10-28 | 2026-10-27 | 2026-10-07 | 2026-09-30 | 2026-09-26 | 2026-09-25 | 2026-09-18 | 2026-09-06 | 2026-08-27
D11 | Mar | Collection | 134 | 2027-03-18 | 2027-01-29 | 2027-02-26 | 2027-02-12 | 2027-02-17 | 2027-02-26 | 2027-03-03 | 2027-01-20 | 2027-01-06 | 2026-12-23 | 2026-11-26 | 2026-11-12 | 2026-10-29 | 2026-11-19 | 2026-11-12 | 2026-11-11 | 2026-11-10 | 2026-10-21 | 2026-10-14 | 2026-10-10 | 2026-09-25 | 2026-09-18 | 2026-09-06 | 2026-08-27
D12 | Mar | - | 28 | 2027-03-25 | 2027-02-05 | 2027-03-05 | 2027-02-19 | 2027-02-24 | 2027-03-05 | 2027-03-10 | 2027-01-27 | 2027-01-13 | 2026-12-30 | 2026-12-03 | 2026-11-19 | 2026-11-05 | 2026-11-26 | 2026-11-19 | 2026-11-11 | 2026-11-10 | 2026-10-21 | 2026-10-14 | 2026-10-10 | 2026-09-25 | 2026-09-18 | 2026-09-06 | 2026-08-27
D13 | Apr | Essentials | 0 | 2027-04-01 | 2027-02-12 | 2027-03-12 | 2027-02-26 | 2027-03-03 | 2027-03-12 | 2027-03-17 | 2027-02-03 | 2027-01-20 | 2027-01-06 | 2026-12-10 | 2026-11-26 | 2026-11-12 | 2026-12-03 | 2026-11-26 | 2026-11-25 | 2026-11-24 | 2026-11-04 | 2026-10-28 | 2026-10-24 | 2026-10-23 | 2026-10-16 | 2026-10-04 | 2026-09-24
D14 | Apr | - | 124 | 2027-04-08 | 2027-02-19 | 2027-03-19 | 2027-03-05 | 2027-03-10 | 2027-03-19 | 2027-03-24 | 2027-02-10 | 2027-01-27 | 2027-01-13 | 2026-12-17 | 2026-12-03 | 2026-11-19 | 2026-12-10 | 2026-12-03 | 2026-11-25 | 2026-11-24 | 2026-11-04 | 2026-10-28 | 2026-10-24 | 2026-10-23 | 2026-10-16 | 2026-10-04 | 2026-09-24
D15 | Apr | Collection | 134 | 2027-04-15 | 2027-02-26 | 2027-03-26 | 2027-03-12 | 2027-03-17 | 2027-03-26 | 2027-03-31 | 2027-02-17 | 2027-02-03 | 2027-01-20 | 2026-12-24 | 2026-12-10 | 2026-11-26 | 2026-12-17 | 2026-12-10 | 2026-12-09 | 2026-12-08 | 2026-11-18 | 2026-11-11 | 2026-11-07 | 2026-10-23 | 2026-10-16 | 2026-10-04 | 2026-09-24
D16 | Apr | - | 28 | 2027-04-22 | 2027-03-05 | 2027-04-02 | 2027-03-19 | 2027-03-24 | 2027-04-02 | 2027-04-07 | 2027-02-24 | 2027-02-10 | 2027-01-27 | 2026-12-31 | 2026-12-17 | 2026-12-03 | 2026-12-24 | 2026-12-17 | 2026-12-09 | 2026-12-08 | 2026-11-18 | 2026-11-11 | 2026-11-07 | 2026-10-23 | 2026-10-16 | 2026-10-04 | 2026-09-24
D17 | Apr | Essentials | 0 | 2027-04-29 | 2027-03-12 | 2027-04-09 | 2027-03-26 | 2027-03-31 | 2027-04-09 | 2027-04-14 | 2027-03-03 | 2027-02-17 | 2027-02-03 | 2027-01-07 | 2026-12-24 | 2026-12-10 | 2026-12-31 | 2026-12-24 | 2026-12-23 | 2026-12-22 | 2026-12-02 | 2026-11-25 | 2026-11-21 | 2026-11-20 | 2026-11-13 | 2026-11-01 | 2026-10-22
D18 | May | - | 124 | 2027-05-06 | 2027-03-19 | 2027-04-16 | 2027-04-02 | 2027-04-07 | 2027-04-16 | 2027-04-21 | 2027-03-10 | 2027-02-24 | 2027-02-10 | 2027-01-14 | 2026-12-31 | 2026-12-17 | 2027-01-07 | 2026-12-31 | 2026-12-23 | 2026-12-22 | 2026-12-02 | 2026-11-25 | 2026-11-21 | 2026-11-20 | 2026-11-13 | 2026-11-01 | 2026-10-22
D19 | May | Collection | 134 | 2027-05-13 | 2027-03-26 | 2027-04-23 | 2027-04-09 | 2027-04-14 | 2027-04-23 | 2027-04-28 | 2027-03-17 | 2027-03-03 | 2027-02-17 | 2027-01-21 | 2027-01-07 | 2026-12-24 | 2027-01-14 | 2027-01-07 | 2027-01-06 | 2027-01-05 | 2026-12-16 | 2026-12-09 | 2026-12-05 | 2026-11-20 | 2026-11-13 | 2026-11-01 | 2026-10-22
D20 | May | - | 28 | 2027-05-20 | 2027-04-02 | 2027-04-30 | 2027-04-16 | 2027-04-21 | 2027-04-30 | 2027-05-05 | 2027-03-24 | 2027-03-10 | 2027-02-24 | 2027-01-28 | 2027-01-14 | 2026-12-31 | 2027-01-21 | 2027-01-14 | 2027-01-06 | 2027-01-05 | 2026-12-16 | 2026-12-09 | 2026-12-05 | 2026-11-20 | 2026-11-13 | 2026-11-01 | 2026-10-22
D21 | May | Essentials | 0 | 2027-05-27 | 2027-04-09 | 2027-05-07 | 2027-04-23 | 2027-04-28 | 2027-05-07 | 2027-05-12 | 2027-03-31 | 2027-03-17 | 2027-03-03 | 2027-02-04 | 2027-01-21 | 2027-01-07 | 2027-01-28 | 2027-01-21 | 2027-01-20 | 2027-01-19 | 2026-12-30 | 2026-12-23 | 2026-12-19 | 2026-12-18 | 2026-12-11 | 2026-11-29 | 2026-11-19
D22 | Jun | - | 124 | 2027-06-03 | 2027-04-16 | 2027-05-14 | 2027-04-30 | 2027-05-05 | 2027-05-14 | 2027-05-19 | 2027-04-07 | 2027-03-24 | 2027-03-10 | 2027-02-11 | 2027-01-28 | 2027-01-14 | 2027-02-04 | 2027-01-28 | 2027-01-20 | 2027-01-19 | 2026-12-30 | 2026-12-23 | 2026-12-19 | 2026-12-18 | 2026-12-11 | 2026-11-29 | 2026-11-19
D23 | Jun | Collection | 134 | 2027-06-10 | 2027-04-23 | 2027-05-21 | 2027-05-07 | 2027-05-12 | 2027-05-21 | 2027-05-26 | 2027-04-14 | 2027-03-31 | 2027-03-17 | 2027-02-18 | 2027-02-04 | 2027-01-21 | 2027-02-11 | 2027-02-04 | 2027-02-03 | 2027-02-02 | 2027-01-13 | 2027-01-06 | 2027-01-02 | 2026-12-18 | 2026-12-11 | 2026-11-29 | 2026-11-19
D24 | Jun | - | 28 | 2027-06-17 | 2027-04-30 | 2027-05-28 | 2027-05-14 | 2027-05-19 | 2027-05-28 | 2027-06-02 | 2027-04-21 | 2027-04-07 | 2027-03-24 | 2027-02-25 | 2027-02-11 | 2027-01-28 | 2027-02-18 | 2027-02-11 | 2027-02-03 | 2027-02-02 | 2027-01-13 | 2027-01-06 | 2027-01-02 | 2026-12-18 | 2026-12-11 | 2026-11-29 | 2026-11-19
D25 | Jun | Essentials | 0 | 2027-06-24 | 2027-05-07 | 2027-06-04 | 2027-05-21 | 2027-05-26 | 2027-06-04 | 2027-06-09 | 2027-04-28 | 2027-04-14 | 2027-03-31 | 2027-03-04 | 2027-02-18 | 2027-02-04 | 2027-02-25 | 2027-02-18 | 2027-02-17 | 2027-02-16 | 2027-01-27 | 2027-01-20 | 2027-01-16 | 2027-01-15 | 2027-01-08 | 2026-12-27 | 2026-12-17
D26 | Jul | - | 124 | 2027-07-01 | 2027-05-14 | 2027-06-11 | 2027-05-28 | 2027-06-02 | 2027-06-11 | 2027-06-16 | 2027-05-05 | 2027-04-21 | 2027-04-07 | 2027-03-11 | 2027-02-25 | 2027-02-11 | 2027-03-04 | 2027-02-25 | 2027-02-17 | 2027-02-16 | 2027-01-27 | 2027-01-20 | 2027-01-16 | 2027-01-15 | 2027-01-08 | 2026-12-27 | 2026-12-17
D27 | Jul | Collection | 134 | 2027-07-08 | 2027-05-21 | 2027-06-18 | 2027-06-04 | 2027-06-09 | 2027-06-18 | 2027-06-23 | 2027-05-12 | 2027-04-28 | 2027-04-14 | 2027-03-18 | 2027-03-04 | 2027-02-18 | 2027-03-11 | 2027-03-04 | 2027-03-03 | 2027-03-02 | 2027-02-10 | 2027-02-03 | 2027-01-30 | 2027-01-15 | 2027-01-08 | 2026-12-27 | 2026-12-17
D28 | Jul | - | 28 | 2027-07-15 | 2027-05-28 | 2027-06-25 | 2027-06-11 | 2027-06-16 | 2027-06-25 | 2027-06-30 | 2027-05-19 | 2027-05-05 | 2027-04-21 | 2027-03-25 | 2027-03-11 | 2027-02-25 | 2027-03-18 | 2027-03-11 | 2027-03-03 | 2027-03-02 | 2027-02-10 | 2027-02-03 | 2027-01-30 | 2027-01-15 | 2027-01-08 | 2026-12-27 | 2026-12-17
Formulas:
Prod start = [Ship 1st]-28
Prod end = [Prod start]+28
Ex-fact 1 = [Ship 1st]-14
Ship 1st = [Ship last]-5
Ship last = [Launch]-15
PO Raise 45 = [Launch]-L2
Blue Seal 2 vendors submission = [PO Raise 105]-7
Techpak to Vendor = [Internal SR]-20
Tech pk handovr to Tech = [Internal SR]-27
Techpack by Design = [Tech pk handovr to Tech]-4
VSR = [Techpack by Design]-1
VSR Working = [VSR]-10
Bottoms Workshop = [VSR]-25
Season Fabric Edit = [Bottoms Workshop]-20
Launch = [Launch, row above]+7
Trevor - SR = [Trevor - SR, row above]
Internal SR = [Trevor - SR]-1